## Consolidated Plan
Project Name /RFP |  | Chemintel
Technology Matrix (Web) |  | Python,Django,MSSQL, React JS
Project Initiated On |  | 20th September 2024 |  |  | Exp. Go Live
Stakeholders |  | Afroze, Ifthiqar Ahmed + Colan Team
Milestone |  | Initiation 20%, Completion of Sanner (J/P) 25%, Completion of DQ 25%, OnePager+NFR 20%, Go-Live 10%
Phase | Task | Description | Duration | Start Date | End Date | Dependencies
Login Section | Login & Logout | Develop the login page | 1 day | 2024-11-18 | 2024-11-18 | Login&logout APIs
| Forgot Password & Verify_Otp | Develop the Forget Password & Verify OTp functionality | 1 day | 2024-11-19 | 2024-11-19 | Forgot Password APIs
| Reset Password & Change Password | Develop the Reset & Change Password functionality | 1 day | 2024-11-20 | 2024-11-20
Product | Create CRUD for Product | Develop CRUD functionalities for APIs | 1 day |  | 2024-11-21 | Figma Design
| Create the ListView | Develop List functionality APIs | 1 day | 2024-11-22 | 2024-11-22 | Figma Design
Customer | Develop the Customer CRUD APIs | Develop CRUD functionalities for APIs | 1 day | 2024-11-25 | 2024-11-25 | Roles&Permission
| Create CRUD for BankDetails | Develop CRUD functionalities for APIs | 1 day | 2024-11-26 | 2024-11-26 | Roles&Permission
| Develop the ListView & Integrate with apis for Customer and Bankdetails | Develop the List functionalities for APIs | 1 day | 2024-11-27 | 2024-11-27
Supplier | Develop the Supplier CRUD APIs | Develop CRUD functionalities for APIs | 1 day | 2024-11-28 | 2024-11-28 | Figma Design
| Create the ListView with pagination | Develop List functionalities for APIs | 1 day | 2024-11-29 | 2024-11-29 | Figma Design
Proposal | Create CRUD for Proposal | Develop CRUD functionalities for APIs | 1 day | 2024-12-02 | 2024-12-02 | List Event Management APIs
| Create the ListView with pagination | Develop the List functionalities for APIs | 1 day | 2024-12-03 | 2024-12-03 | Figma Design
Roles & Permission | Create Roles | Manage Roles&permission | 1 day | 2024-12-04 | 2024-12-04 | Completion of each respective phase
|  | Develop the User permission View | 1 day | 2024-12-05 | 2024-12-05 | Unit Testing
Mobile App Development for Chat | Firebase Account setup
Mobile App development
API development
Cloud Function setup for push notification
Webhook development for handleing the message
Desktop App Development for Chat
WhatsApp Account setup
Email Account Setup
Read WhatsApp Message
Read Email Message
Send WhatsApp Message
Send Email Message

## FE Implementation
Phase | Task Description | Duration | Start Date | End Date | Dependencies (If any)
Login Section | Implement the Login page UI and functionality. |  | 2024-11-21 | 2024-11-21
| Implement the Forget Password flow, including Verify OTP functionality. |  | 2024-11-21 | 2024-11-22
| Implement Reset & Change Password functionality. |  | 2025-11-25 | 2025-11-25
Product | Integrate CRUD operations for various data entities using APIs. |  | 2024-11-26 | 2024-11-26
| Integrate List display functionality using APIs. |  | 2024-11-27 | 2024-11-27
Customer | Integrate CRUD functionalities using APIs |  | 2024-11-28 | 2024-11-29
| Integrate CRUD functionalities using APIs |  | 2024-12-02 | 2024-12-02
| Develop the List functionalities for APIs |  | 2024-12-03 | 2024-12-03
Supplier | Integrate CRUD functionalities using APIs |  | 2024-12-04 | 2024-12-04
| Integrate CRUD functionalities using APIs |  | 2024-12-05 | 2024-12-05
Proposal | Integrate CRUD functionalities using APIs |  | 2024-12-06 | 2024-12-07
| Integrate CRUD functionalities using APIs |  | 2024-12-09 | 2024-12-09
Roles & Permission | Build Role & Permission management UI. |  | 2024-12-10 | 2024-12-11
| Implement the User Permission View UI with proper styling and API integration. |  | 2024-12-12 | 2024-12-13
Mobile App Development for Chat
Desktop App Development for Chat
WhatsApp Account setup
Email Account Setup
Read WhatsApp Message
Read Email Message
Send WhatsApp Message
Send Email Message